## Tabelle1
Arbeitspakete / Kalenderwoche | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Homogeneous notation
Placement of objects and camera
Scene file parsing
Implicit surfaces, Parametric surfaces
Bounding Volume AABBs
Phong
Shadows (point & directional light)
Sampling (random, stratified, poisson, halton)
Box-, Mitchell-filter
Milestone: Working raytracer
Acceleration: BVH, grid, kd-tree, octree
BRDF
Transparency, refraction (BTDF)
Acceleration vs. Quality: Monte-Carlo
Dynamic Sampling
Camera models: Depth-of-field
Area light
Ambient occlusion
Milestone: End of project - presentation